## Risk Management Dashboard
Project Name: |  | ABC
Client
Report Date : |  | 2026-03-02
[10 empty] | no | match
[10 empty] | 1 | 7
[10 empty] | 2 | 4
[10 empty] | 3 | 1
| ID | Risk Description | Score | Impact vs Probability | [5 empty] | 4 | 5
|  | D 19 | 20 | [6 empty] | 5 | 6
| 9 | D 9 | 10 | [6 empty] | 6 | 3 | [6 empty] | settings
| 1 | D 1 | 9 |  | 0 | 0 | 0 | 0 | 0 | 7 |  | 0 | 0 | 0 | 0 | 0
| 11 | D 11 | 9 |  | 0 | 0 | 0 | 0 | 0 | 8 |  | 0 | 0 | 0 | 0 | 0
| 14 | D 14 | 6 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
| 6 | D 6 | 3 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
PMBOK - 135
[12 empty] | Avoid | Changing the project plan to eliminate the risk.
[12 empty] | Transfer | Seek to shift the consequence of risk to a 3rd party together with ownership and response
[12 empty] | Mitigate | Mitigation seeks to reduce the probability and impact of a risk event to an acceptable threshold. Taking early action to reduce the probability or impact is more effective than trying to repair the consequences after it has occurred.
[12 empty] | Accept | Indicates that the project team has decided not to change the project plan to deal with a risk or is unable to identify any other suitable response strategy.
[17 empty] | CHECK VALUE | MAX | SLICES | DEGREES | X | Y
[17 empty] | 9.5 | 25 | 5% | 111.6 | 0 | 0 |  | Remaining risk | 6
[19 empty] | 5% |  | -0.36812 | 0.92978 |  | Clsoed | 1
5%
5%
5%
5%
5%
5%
5%
5%
50%
RISK PRIORITY
[25 empty] | Current Status / Priority | Critical | High | Moderate | Tolerable | Negligible | Total | % Of Total
[24 empty] | STATUS | Closed | 0 | 0 | 1 | 0 | 0 | 1 | 14.29%
[25 empty] | In-Progress | 0 | 0 | 2 | 0 | 0 | 2 | 28.57%
[25 empty] | Behind | 0 | 1 | 0 | 1 | 1 | 3 | 42.86%
[25 empty] | Not Started | 0 | 0 | 1 | 0 | 0 | 1 | 14.29%
[25 empty] | Total | 0 | 1 | 4 | 1 | 1 | 7 | 100%
[22 empty] | Not Started | 1 |  | % of Total | 0% | 14.29% | 57.14% | 14.29% | 14.29% | 85.71%
[22 empty] | In-Progress | 5
[22 empty] | Closed | 1 |  |  | Critical | High | Moderate | Tolerable | Negligible
[25 empty] | Remaining | 0 | 1 | 3 | 1 | 1
[26 empty] | 0 Very High | 0 High Risk | 0 Medium Risk | 0 Low Risk | 0 Very Low Risk | total
[26 empty] | 0 | 0 | 0 | 0 | 0 | 0
[26 empty] | 0 | 0 | 0 | 0 | 0 | 0
[26 empty] | 0 | 0 | 0 | 0 | 0 | 0
[26 empty] | 0 | 0 | 0 | 0 | 0 | 0
[26 empty] | 0 | 0 | 0 | 0 | 0 | 0
[26 empty] | 0 | 0 | 0 | 0 | 0 | 0
[26 empty] | 0 | 0 | 0 | 0 | 0 | 0
[26 empty] | 0 | 0 | 0 | 0 | 0
[25 empty] | Avoid | 0 | 0 | 1 | 0 | 0
[25 empty] | Escalate | 0 | 0 | 0 | 0 | 1
[25 empty] | Transfer | 0 | 0 | 0 | 1 | 0
[25 empty] | Mitigate | 0 | 0 | 2 | 0 | 0
[25 empty] | Accept | 0 | 1 | 0 | 0 | 0
[26 empty] | 0 Very High | 0 High Risk | 0 Medium Risk | 0 Low Risk | 0 Very Low Risk | total
[26 empty] | 0 | 0 | 0 | 0 | 0 | 0
[26 empty] | 0 | 0 | 0 | 0 | 0 | 0
[26 empty] | 0 | 0 | 0 | 0 | 0 | 0
[26 empty] | 0 | 0 | 0 | 0 | 0 | 0
[26 empty] | 0 | 0 | 0 | 0 | 0 | 0
[26 empty] | 0 | 0 | 0 | 0 | 0 | 0
[26 empty] | 0 | 0 | 0 | 0 | 0 | 0
[26 empty] | 0 | 0 | 0 | 0 | 0 | 0
[26 empty] | 0 | 0 | 0 | 0 | 0 | 0

## Risk Register
ID | Helper_Row | Risk Description | Risk Effect on Objectives | Impact Area | Impact Category | Impact Rating | Probability | Risk Score | Risk Priority | Risk Ranking | Status | Risk Owner | Date Raised | Closed Date | Mitigation Strategy | Risk Response
1 | 2 | D 1 | Impact and Effect 1 | Cost | Cost | Moderate | Average | 9 | Moderate | 3 | Not Started | Owner 1 | 2025-12-01 |  | Mitigate
4 | 5 | D 4 | Impact and Effect 4 | Security/Compliance | Security/Compliance | Minor | Very High | 10 | Moderate |  | Closed | Owner 4 | 2026-01-17 | 2026-01-27 | Accept
6 | 7 | D 6 | Impact and Effect 6 | Security/Compliance | Security/Compliance | Moderate | Very Low | 3 | Negligible | 6 | Behind | Owner 6 | 2026-01-31 |  | Escalate
9 | 10 | D 9 | Impact and Effect 9 | Schedule | Schedule | Minor | Very High | 10 | Moderate | 2 | In-Progress | Owner 9 | 2026-02-21 |  | Avoid
11 | 12 | D 11 | Impact and Effect 11 | Cost | Cost | Moderate | Average | 9 | Moderate | 4 | In-Progress | Owner 11 | 2026-01-24 |  | Mitigate
14 | 15 | D 14 | Impact and Effect 14 | Other | Other | Minor | Average | 6 | Tolerable | 5 | Behind | Owner 3 | 2026-02-14 |  | Transfer
| 20 | D 19 | Impact and Effect 19 | Other | Other | Major | Very High | 20 | High | 1 | Behind | Owner 8 | 2026-02-28 |  | Accept
Formulas:
Date Raised = IF([Helper_Row]="","",IF(IFERROR(INDEX('RAID Log'!$1:$1048576,[Helper_Row],MATCH("Date Raised",'RAID Log'!$1:$1,0)),"")="","",IFERROR(INDEX('RAID Log'!$1:$1048576,[Helper_Row],MATCH("Date Raised",'RAID Log'!$1:$1,0)),"")))
Closed Date = IF([Helper_Row]="","",IF(IFERROR(INDEX('RAID Log'!$1:$1048576,[Helper_Row],MATCH("Closed Date",'RAID Log'!$1:$1,0)),"")="","",IFERROR(INDEX('RAID Log'!$1:$1048576,[Helper_Row],MATCH("Closed Date",'RAID Log'!$1:$1,0)),"")))

## RAID Log
RAID ID | Type | Category | Impact Area | Title | Description | Impact/Effect of the RAID | Date Raised | RAID Owner | Impact Rating | Initial Probability | Severity | Target Date | Status | Mitigation Strategy | Next Update | Closed Date | RAID Response/Plan | Risk Seq
1 | Risk | Quality | Cost | Title 1 | D 1 | Impact and Effect 1 | 2025-12-01 | Owner 1 | Moderate | Average | High |  | Not Started | Mitigate | 2026-03-14 |  |  | 1
2 | Assumption | Cost | Other | Title 2 | D 2 | Impact and Effect 2 | 2026-01-03 | Owner 2 | Severe | High | Medium |  | Behind | Transfer | 2026-03-16
3 | Dependency | Stakeholder | Schedule | Title 3 | D 3 | Impact and Effect 3 | 2026-01-10 | Owner 3 | Insignificant | Very High | Medium |  | In-Progress | Escalate | 2026-03-16
4 | Risk | Security/Compliance | Security/Compliance | Title 4 | D 4 | Impact and Effect 4 | 2026-01-17 | Owner 4 | Minor | Very High | Critical |  | Closed | Accept | 2026-03-17 | 2026-01-27 |  | 2
5 | Issue | Scope | Schedule | Title 5 | D 5 | Impact and Effect 5 | 2026-01-24 | Owner 5 | Major | Average | Low |  | Not Started | Mitigate | 2026-03-16
6 | Risk | Stakeholder | Security/Compliance | Title 6 | D 6 | Impact and Effect 6 | 2026-01-31 | Owner 6 | Moderate | Very Low | High |  | Behind | Escalate | 2026-03-16 |  |  | 3
7 | Assumption | Security/Compliance | Cost | Title 7 | D 7 | Impact and Effect 7 | 2026-02-07 | Owner 7 | Severe | Average | Medium |  | Not Started | Transfer | 2026-03-20
8 | Dependency | Scope | Other | Title 8 | D 8 | Impact and Effect 8 | 2026-02-14 | Owner 8 | Insignificant | High | Medium |  | Behind | Avoid | 2026-03-16
9 | Risk | Technical | Schedule | Title 9 | D 9 | Impact and Effect 9 | 2026-02-21 | Owner 9 | Minor | Very High | Critical |  | In-Progress | Avoid | 2026-03-13 |  |  | 4
10 | Issue | Process | Security/Compliance | Title 10 | D 10 | Impact and Effect 10 | 2026-02-28 | Owner 10 | Major | Very High | Low |  | In-Progress | Accept | 2026-03-26 | 2026-03-10
11 | Risk | Process | Cost | Title 11 | D 11 | Impact and Effect 11 | 2026-01-24 | Owner 11 | Moderate | Average | High |  | In-Progress | Mitigate | 2026-04-05 |  |  | 5
12 | Assumption | Resource | Other | Title 12 | D 12 | Impact and Effect 12 | 2026-01-31 | Owner 12 | Severe | Very Low | Medium |  | Closed | Accept | 2026-03-16 | 2026-02-10
13 | Dependency | Scope | Quality | Title 13 | D 13 | Impact and Effect 13 | 2026-02-07 | Owner 2 | Insignificant | High | Medium |  | Not Started | Transfer | 2026-03-16
14 | Risk | Stakeholder | Other | Title 14 | D 14 | Impact and Effect 14 | 2026-02-14 | Owner 3 | Minor | Average | Critical |  | Behind | Transfer | 2026-03-23 |  |  | 6
15 | Issue | Resource | Quality | Title 15 | D 15 | Impact and Effect 15 | 2026-02-21 | Owner 4 | Major | Very Low | Low |  | Closed | Accept | 2026-03-16 | 2026-03-03
16 | Dependency | Stakeholder | Cost | Title 16 | D 16 | Impact and Effect 16 | 2026-02-28 | Owner 16 | Insignificant | Very High | High |  | In-Progress | Accept | 2026-03-28 | 2026-03-10
17 | Assumption | Resource | Other | Title 17 | D 17 | Impact and Effect 17 | 2026-02-14 | Owner 10 | Severe | Average | Medium |  | Behind | Transfer | 2026-03-16
| Dependency | Scope | Quality | Title 18 | D 18 | Impact and Effect 18 | 2026-02-21 | Owner 11 | Moderate | High | Medium |  | In-Progress | Transfer | 2026-03-23
| Risk | Stakeholder | Other | Title 19 | D 19 | Impact and Effect 19 | 2026-02-28 | Owner 8 | Major | Very High | Critical |  | Behind | Accept | 2026-03-16 |  |  | 7
| Issue | Resource | Quality | Title 20 | D 20 | Impact and Effect 20 | 2026-01-24 | Owner 9 | Insignificant | Very High | Low |  | Closed | Accept | 2026-03-28
17 | Assumption | Resource | Other | Title 17 | D 17 | Impact and Effect 17 | 2026-02-14 | Owner 10 | Severe | Average | Medium |  | Behind | Transfer | 2026-03-16
17 | Assumption | Resource | Other | Title 17 | D 17 | Impact and Effect 17 | 2026-02-14 | Owner 10 | Severe | Average | Medium |  | Behind | Transfer | 2026-03-16
17 | Assumption | Resource | Other | Title 17 | D 17 | Impact and Effect 17 | 2026-02-14 | Owner 10 | Severe | Average | Medium |  | Behind | Transfer | 2026-03-16
17 | Assumption | Resource | Other | Title 17 | D 17 | Impact and Effect 17 | 2026-02-14 | Owner 10 | Severe | Average | Medium |  | Behind | Transfer | 2026-03-16
17 | Assumption | Resource | Other | Title 17 | D 17 | Impact and Effect 17 | 2026-02-14 | Owner 10 | Severe | Average | Medium |  | Behind | Transfer | 2026-03-16
Formulas:
Closed Date = 'RAID Log'!$[Date Raised]+10

## RAID Dashboard
RAID Dashboard
Total RAIDs |  | Risks | Assumptions |  | Issues |  | Dependencies |  | RAID Dashboard
[9 empty] | Select RAID Type | Risk
25 |  | 7 | 9 |  | 4 |  | 5
| Status | Count | Category | Count |  | Mitigation | Count
| Not Started | 1 | Cost | 0 |  | Avoid | 1
| In-Progress | 2 | Process | 1 |  | Mitigate | 2
| Behind | 3 | Quality | 1 |  | Transfer | 1
| Closed | 1 | Resource | 0 |  | Escalate | 1
|  |  | Scope | 0 |  | Accept | 2 |  |  |  | Category Label Compact | Count Compact
|  |  | Security/Compliance | 1
|  |  | Stakeholder | 3
|  |  | Technical | 1
| Status Label | Count | Mitigation Label | Count |  |  | Category Label | Count
| Not Started | 1 | Avoid | 1
| In-Progress | 2 | Mitigate | 2 |  |  | Process | 1
| Behind | 3 | Transfer | 1 |  |  | Quality | 1
| Closed | 1 | Escalate | 1
|  |  | Accept | 2
[7 empty] | Security/Compliance | 1
[7 empty] | Stakeholder | 3
[7 empty] | Technical | 1

## RAID Insights
RAID Insights | [7 empty] | Filter | RAID Type
Risk
Total Open RAIDs | Overdue Issues | Open Risks |  |  | Open Issues |  |  | Open Dependencies |  | Overdue Bucket | Count | Age Bucket | Count
20 | 0 | 6 |  |  | 2 |  |  | 5 |  | 1-7 days | 0 | 0-7 days | 0
[10 empty] | 8-14 days | 0 | 8-14 days | 1
[10 empty] | 15-30 days | 0 | 15-30 days | 2
Operational Analytics | [9 empty] | 30+ days | 0 | 31-60 days | 2
[12 empty] | 60+ days | 1
[10 empty] | Risk Owner | Open Risks
[10 empty] | Owner 1 | 1
[10 empty] | Owner 6 | 1
[10 empty] | Owner 9 | 1
[10 empty] | Owner 11 | 1
[10 empty] | Owner 3 | 1
Risk Analytics |  | Risk Heatmap
|  | Impact \ Probability | Very High | High | Average | Low | Very Low
|  | Severe | 0 | 0 | 0 | 0 | 0
|  | Major | 1 | 0 | 0 | 0 | 0
|  | Moderate | 0 | 0 | 2 | 0 | 1
|  | Minor | 1 | 0 | 1 | 0 | 0
|  | Insignificant | 0 | 0 | 0 | 0 | 0