## RAID Dashboard
RAID Dashboard
Total RAIDs |  | Risks | Assumptions |  | Issues |  | Dependencies |  | RAID Dashboard
[9 empty] | Select RAID Type | Assumption
20 |  | 5 | 4 |  | 6 |  | 5
| Status | Count | Category | Count |  | Mitigation | Count
| Not Started | 0 | Cost | 0 |  | Avoid | 0
| In-Progress | 4 | Process | 1 |  | Mitigate | 0
| Behind | 0 | Quality | 1 |  | Transfer | 0
| Closed | 0 | Resource | 0 |  | Escalate | 0
|  |  | Scope | 0 |  | Accept | 4 |  |  |  | Category Label Compact | Count Compact
|  |  | Security/Compliance | 1
|  |  | Stakeholder | 1
|  |  | Technical | 0
| Status Label | Count | Mitigation Label | Count |  |  | Category Label | Count
#N/A
| In-Progress | 4 |  | #N/A |  |  | Process | 1
|  |  |  | #N/A |  |  | Quality | 1
#N/A
|  |  | Accept | 4
[7 empty] | Security/Compliance | 1
[7 empty] | Stakeholder | 1

## Project Cover Sheet
Project Name
Integrated Project Management Workbook |  |  |  |  | #REF!
Project Overview |  |  | Schedule & Commercials
Project Name | NDC 17.2 to 24.1 Migration - Gap Analysis |  | Start Date | 2025-12-01
Client | Accelya |  | Forecast End | 2026-07-31
Project Manager | Santhosh Nebalan |  | Duration (Days) | 242
Project Sponsor | Mike Douglass |  | Budget | 650000
Complexity | High |  | Benefits | Possible - Phase 2 SOW - For Development on Identified GAPs
Execution Snapshot |  | RAID Snapshot |  | Team & Governance
5 | 2 | 5 | 6 | 12 |  | 9
Total Tasks | Completed | Open Risks | Open Issues | Stakeholders |  | Resources
1 | 3 | 5 | 1 | 0
In Progress | Tracked Milestones | Open Dependencies | Change Requests | Cadences |  | Report Date
Quick Navigation & Notes
Use this sheet as the front page of the workbook. It pulls summary fields from Project Charter and high-level counts from the core tracking tabs. |  |  |  | Go to Project Charter |  | Go to Project Plan
Best practice: update Project Charter first, then maintain Project Plan / RAID / Stakeholder / Resource sheets. The cover sheet will reflect the latest picture.
|  |  |  | Go to RAID Dashboard |  | Go to Risk Register
Single source of truth for charter, schedule, RAID, stakeholders, resources, changes, and milestone tracking.
|  |  |  | Go to Stakeholders |  | Go to Milestones

## Project Charter
NDC 17.2 to 24.1 Migration - Gap Analysis
Project Name: | NDC 17.2 to 24.1 Migration - Gap Analysis |  | Project Manager: | Santhosh Nebalan |  |  | Project Sponsor: | Mike Douglass
Project Start Date: | 2025-12-01 |  | Estimated Duration: | 242 |  |  | Forecast End Date: | 2026-07-31
Estimated Budget: | 650000 |  | Estimated Benefits: | Possible - Phase 2 SOW - For Development on Identified GAPs |  |  | Project Complexity: | High
Business Case: |  |  |  |  | Project Deliverables:
Gap identification between 17.2 & 24.1 for Airlines. Gap identification, documentation, and conversion to user stories/change requests. |  |  |  |  | Gap document Detailed user stories Modified 24.1 test scripts Repository of anonymized 17.2 Request/Response pairs
Scope: |  |  |  |  | Milestones:
Included |  | Excluded |  |  | ID | Milestone Title |  |  | Estimated Start | Estimated Finish
Migrate 6 airlines from NDC 17.2 to NDC 24.1 by 2027 |  | Any code changes, enhancements, or defect fixes identified during testing in Phase 1 will be handled in Phase2 |  |  |  | Project Kick Off |  |  | 2025-12-01 | 2025-12-01
Approach in two phases, Gap analysis and migration to work in parallel |  | Changes to test case framework generator (TCG) not covered in this scope |  |  |  | Onboarding |  |  | 2025-11-29 | 2025-12-01
In Scope Airlines: AA, UA, WY, AM |  | Validation of new NDC 24.1 features not part of existing airline customizations is out of scope. |  |  |  | American Airlines |  |  | 2025-12-01 | 2026-02-28
Production data mirroring and execution of shopping transactions for top agencies using traffic patterns |  | Airlines out of scope: LHG, COPA, ET, OA, A3, DL, KE, TS, 4Z, QF, HA, AS, EK, WS |  |  |  | United Airlines |  |  | 2026-01-01 | 2026-03-31
|  | SPRK, Agency certification |  |  |  | Oman Air |  |  | 2026-04-01 | 2026-05-31
|  | UAT and production deployment |  |  |  | Aero Mexico |  |  | 2026-06-01 | 2026-07-31
Top 3 Risks:
ID | Risk/Issue Description | Risk Rating | Mitigation/Action Plan
| sss | HIGH
MEDIUM
LOW
Project Approval:

## Risk Register
ID | Helper_Row | Risk Description | Risk Effect on Objectives | Impact Area | Impact Category | Impact Rating | Probability | Risk Score | Risk Priority | Risk Ranking | Status | Risk Owner | Date Raised | Closed Date | Mitigation Strategy | Risk Response
1 | 2 | Remaining AA 24.1 scenarios are not fully mapped to test cases. | Partially blocks sample execution, reduces coverage, and creates rework. | Schedule | Schedule | Major | High | 16 | High | 1 | In-Progress | Accelya QA / AA QA | 2026-02-20 |  | Mitigate | Close remaining mappings and confirm acceptance criteria.
2 | 3 | Baseline failures in 17.2 continue to impact execution and retest cycles. | Slows progress, increases retesting effort, and adds schedule pressure. | Schedule | Schedule | Major | High | 16 | High | 2 | Behind | Accelya Engineering | 2026-02-23 |  | Mitigate | Prioritize failure closure and get committed ETAs.
3 | 4 | QA clarifications and closure cycles are not happening fast enough on priority blockers. | Increases schedule slippage risk and delays testcase clearance. | Schedule | Schedule | Major | High | 16 | High | 3 | Behind | Accelya QA | 2026-02-24 |  | Escalate | Increase cadence and improve closure-focused working sessions.
4 | 5 | Required access and readiness for production shopping / live data mirroring are still incomplete. | Delays start of live data mirroring testing and pushes dependent work out. | Schedule | Schedule | Major | High | 16 | High | 4 | In-Progress | Accelya PM / Candice | 2026-02-27 |  | Mitigate | Complete access approvals and confirm readiness inputs.
5 | 6 | Incorrect PCC mapping has forced retesting of impacted test cases. | Completed counts may move back to pending, creating volatility in status reporting. | Schedule | Schedule | Moderate | High | 12 | Moderate | 5 | In-Progress | Zapcom QA | 2026-03-09 |  | Mitigate | Complete retesting and validate corrected mapping before closure.
6
Formulas:
Date Raised = IF([Helper_Row]="","",IF(IFERROR(INDEX('RAID Log'!$1:$1048576,[Helper_Row],MATCH("Date Raised",'RAID Log'!$1:$1,0)),"")="","",IFERROR(INDEX('RAID Log'!$1:$1048576,[Helper_Row],MATCH("Date Raised",'RAID Log'!$1:$1,0)),"")))

## RAID Log
RAID ID | Type | Category | Impact Area | Title | Description | Impact/Effect of the RAID | Date Raised | RAID Owner | Impact Rating | Initial Probability | Severity | Target Date | Status | Mitigation Strategy | Next Update | Closed Date | RAID Response/Plan | Risk Seq
1 | Risk | Scope | Schedule | AA 24.1 scenario-to-TC mapping delay | Remaining AA 24.1 scenarios are not fully mapped to test cases. | Partially blocks sample execution, reduces coverage, and creates rework. | 2026-02-20 | Accelya QA / AA QA | Major | High | High | 2026-03-25 | In-Progress | Mitigate | 2026-03-25 |  | Close remaining mappings and confirm acceptance criteria. | 1
2 | Risk | Technical | Schedule | 17.2 baseline failures slowing execution | Baseline failures in 17.2 continue to impact execution and retest cycles. | Slows progress, increases retesting effort, and adds schedule pressure. | 2026-02-23 | Accelya Engineering | Major | High | High | 2026-03-31 | Behind | Mitigate | 2026-03-25 |  | Prioritize failure closure and get committed ETAs. | 2
3 | Risk | Process | Schedule | Slow QA turnaround and closure cycles | QA clarifications and closure cycles are not happening fast enough on priority blockers. | Increases schedule slippage risk and delays testcase clearance. | 2026-02-24 | Accelya QA | Major | High | High | 2026-03-25 | Behind | Escalate | 2026-03-25 |  | Increase cadence and improve closure-focused working sessions. | 3
4 | Risk | Security/Compliance | Schedule | Production shopping access and readiness delay | Required access and readiness for production shopping / live data mirroring are still incomplete. | Delays start of live data mirroring testing and pushes dependent work out. | 2026-02-27 | Accelya PM / Candice | Major | High | High | 2026-03-25 | In-Progress | Mitigate | 2026-03-25 |  | Complete access approvals and confirm readiness inputs. | 4
5 | Risk | Quality | Schedule | PCC mapping rework distorting progress counts | Incorrect PCC mapping has forced retesting of impacted test cases. | Completed counts may move back to pending, creating volatility in status reporting. | 2026-03-09 | Zapcom QA | Moderate | High | High | 2026-03-25 | In-Progress | Mitigate | 2026-03-25 |  | Complete retesting and validate corrected mapping before closure. | 5
6 | Assumption | Stakeholder | Schedule | Accelya and AA QA will close remaining 3 mappings | Assumes the remaining unmapped scenarios will receive support from Accelya / AA QA. | Without this support, AA 24.1 sample execution cannot be fully unblocked. | 2026-03-18 | Accelya QA / AA QA | Major | Average | Medium | 2026-03-25 | In-Progress | Accept | 2026-03-25 |  | Secure owners and ETA for the remaining mappings.
7 | Assumption | Process | Schedule | Accelya non-QA owners will improve Jira closure pace | Assumes the non-QA lane will review and respond to the Jira backlog at an improved cadence. | Needed to reduce open ticket backlog and prevent further schedule drag. | 2026-03-18 | Accelya Non-QA Owners | Major | Average | Medium | 2026-03-31 | In-Progress | Accept | 2026-03-25 |  | Commit to a weekly throughput target and publish ETAs.
8 | Assumption | Security/Compliance | Schedule | Remaining production access for 2 users will be granted | Assumes pending access approvals for remaining users will be completed. | Without access, production shopping activities cannot fully proceed. | 2026-03-18 | Accelya PM / Candice | Major | Average | Medium | 2026-03-25 | In-Progress | Accept | 2026-03-25 |  | Confirm access approvals and dates for the remaining users.
9 | Assumption | Quality | Other | Retest-driven count changes will be accepted as valid | Assumes weekly metric movements caused by retesting will be treated as valid execution corrections. | Prevents misreading progress volatility caused by PCC correction work. | 2026-03-18 | Zapcom QA Lead | Moderate | Average | Low | 2026-03-25 | In-Progress | Accept | 2026-03-25 |  | Call out retest-driven moves in the weekly narrative to avoid confusion.
10 | Issue | Process | Schedule | 44 open Jira tickets pending Accelya review | Open Jira backlog is awaiting review, resolution, or ETA from Accelya non-QA owners. | Blocks testcase progression and keeps execution dependent on external turnaround. | 2026-03-17 | Accelya Non-QA Owners | Severe | High | Critical | 2026-03-31 | Behind | Escalate | 2026-03-25 |  | Drive committed review cadence and publish clear ETAs on prioritized tickets.
11 | Issue | Quality | Schedule | 48 TCs blocked on Accelya QA clarification | Test cases are blocked pending QA clarification or decision from Accelya QA. | Directly delays testcase closure and milestone movement. | 2026-03-17 | Accelya QA | Severe | High | Critical | 2026-03-25 | Behind | Escalate | 2026-03-25 |  | Work priority list with ETAs; convert clarifications into worked closures.
12 | Issue | Process | Schedule | Weekly QA meeting cadence is not converting to worked closures | Current 45-minute weekly QA session is not producing enough actual worked outcomes. | Reviewed items are not translating into closure at the needed rate. | 2026-03-17 | Accelya QA / Zapcom QA | Major | High | High | 2026-03-25 | Behind | Mitigate | 2026-03-25 |  | Move to 2x weekly working sessions and track “worked” conversion.
13 | Issue | Scope | Quality | 3 remaining AA 24.1 scenarios still need TC mapping | Final scenarios still require testcase mapping support for AA 24.1 samples. | Leaves part of sample coverage incomplete and partially blocked. | 2026-03-06 | Accelya QA / AA QA | Major | High | High | 2026-03-25 | In-Progress | Mitigate | 2026-03-25 |  | Close final mappings and confirm coverage completion.
14 | Issue | Technical | Schedule | Live Data Mirroring Testing not started | Production-shopping-based mirroring work has not started because prerequisites are incomplete. | Delays a dependent testing stream and compresses the future execution window. | 2026-03-17 | Accelya PM / Candice | Major | High | High | 2026-03-28 | Behind | Mitigate | 2026-03-25 |  | Finish access and confirm test input mapping to start execution.
15 | Issue | Quality | Schedule | Incorrect PCC mapping triggered retesting | Some executed test cases must be retested due to earlier PCC mapping errors. | Causes rework and legitimate movement between completed and pending counts. | 2026-03-10 | Zapcom QA | Major | High | High | 2026-03-25 | In-Progress | Mitigate | 2026-03-25 |  | Retest impacted cases and refresh status counts after validation.
16 | Dependency | Stakeholder | Schedule | Accelya and AA QA support for final scenario mapping | Completion of remaining mapping depends on support from Accelya and AA QA. | AA 24.1 sample execution cannot be fully completed without this dependency. | 2026-03-18 | Accelya QA / AA QA | Major | High | High | 2026-03-25 | In-Progress | Mitigate | 2026-03-25 |  | Confirm owners and ETAs for the remaining mappings.
17 | Dependency | Process | Schedule | Accelya non-QA review and ETA on Jira backlog | Jira backlog clearance depends on review and ETA commitments from Accelya non-QA owners. | Execution remains blocked until ticket responses and closures move faster. | 2026-03-18 | Accelya Non-QA Owners | Severe | High | Critical | 2026-03-31 | Behind | Escalate | 2026-03-25 |  | Commit to ~20 tickets/week reviewed with resolution or ETA.
18 | Dependency | Quality | Schedule | Accelya QA clarification and decision cycle | Blocked testcase resolution depends on Accelya QA clarifications and expected-behavior decisions. | Without timely QA input, testcase closure rate stays low. | 2026-03-18 | Accelya QA | Severe | High | Critical | 2026-03-25 | Behind | Escalate | 2026-03-25 |  | Provide proactive QA support with ETAs on prioritized items.
19 | Dependency | Security/Compliance | Schedule | Production access for remaining users | Production-shopping work depends on remaining user access being approved and enabled. | Prevents full start of production-based testing activities. | 2026-03-18 | Accelya PM / Candice | Major | High | High | 2026-03-25 | In-Progress | Mitigate | 2026-03-25 |  | Complete remaining access approvals and confirm dates.
20 | Dependency | Technical | Schedule | Scenario and TC identification for production shopping | Live data mirroring depends on confirmed production shopping scenarios and testcase identification. | Even with access, execution cannot start cleanly without finalized inputs. | 2026-03-18 | Zapcom QA / Accelya QA | Major | High | High | 2026-03-25 | In-Progress | Mitigate | 2026-03-25 |  | Finalize scenarios and TC identification needed to start mirroring.

## Stakeholder Register
Sr. No. | Name | Designation | Department | Role | Contact | Category | Interest | Influence | Category (Auto) | Expectations | Communication Type | Communication Frequency | Comms frequency | Comments
1 | Candice Cobaugh | Specialist - Release Engineering | Project Management | Project Manager | candice.cobaugh@accelya.com | External | 3 | 2 | Monitor |  | Email |  | Daily
2 | Densey Davis-Lumsden | Vice President - Customer Success | Customer Success | CSM | densey.davis-lumsden@accelya.com | External | 2 | 4 | Keep Satisfied |  | Email |  | Daily
3 | Mike Douglass | Chief of Global Programs | Global Programs | Project Sponsor | mike.douglass@accelya.com | External | 1 | 5 | Keep Satisfied |  | Email |  | Monthly
4 | Gunilla Gunness | Principal - NDC Adoption | NDC | SME | gunilla.gunness@accelya.com | External | 4 | 3 | Keep Informed |  | Email |  | Daily
5 | Astryd Rodriguez | Senior Specialist - Product Owner | Product Engineering | SME | astryd.rodriguez@accelya.com | External | 2 | 3 | Monitor |  | Email |  | Daily
6 | Anushree Rao | Team Lead - Quality Assurance | Customer Engineering Airline Retailing | QA Lead | anushree.rao@accelya.com | External | 1 | 1 | Monitor |  | Email |  | Daily
7 | Suraj Tajane | Engineer II - Implementation QA | Customer Engineering Airline Retailing | QA | suraj.tajane@accelya.com | External | 1 | 1 | Monitor |  | Email |  | Daily
8 | Bryan St. Louis | Specialist - Solution Engineering | Solution Engineering | BA | bryan.stlouis@accelya.com | External | 4 | 4 | Manage Closely |  |  |  | Daily
9 | Debashree Das | Customer success manager | Customer Success | CSM | debashree.das@zapcg.com | Internal | [6 empty] | Daily
10 | Sneha Reddy | Sr. Data Analyst | Product Engineering | Product Owner | Snehareddy@zapcg.com | Internal
11 | Sravanthi Palavalli | Lead SDET | Engineering | QA Lead | sravanthi.palavalli@zapcg.com | Internal
12 | Santhosh Nebalan | Program Manager | Project Management | Project Manager | santhosh.nebalan@zapcg.com | Internal

## PM_Lists (hidden)
CadenceType | Frequency | GenericStatus | ResourceStatus | Criticality | Priority | ChangeStatus | Decision | UnavailabilityType | ImpactLevel | AvailabilityStatus | TaskType | ProjectPlanStatus | RAGStatus | MilestoneFlag | ProjectPhase
Governance | Daily | Planned | Requested | Critical | Critical | Submitted | Pending | Vacation | High | Planned | Task | Not Started | Red | ☐ | Initiation
Agile Ceremony | Weekly | Active | Confirmed | High | High | Under Review | Approved | Holiday | Medium | Approved | Milestone | In Progress | Amber | ☑ | Planning
Delivery Review | Bi-weekly | On Hold | Active | Medium | Medium | Approved | Rejected | Sick Leave | Low | Completed | Review | On Hold | Green |  | Execution
Working Session | Monthly | Closed | Rolled Off | Low | Low | Rejected | Deferred | Training |  | Cancelled | Decision | Completed |  |  | Testing
Leadership Review | Quarterly |  | Backfill Needed |  |  | Implemented |  | Partial Availability |  |  | Dependency | Delayed |  |  | UAT
| Once |  |  |  |  | Closed |  | Other |  |  |  | Cancelled |  |  | Deployment
| As Needed |  |  |  |  | Deferred | [8 empty] | Hypercare
Closure

## Governance & Cadences
Cadence ID | Forum / Meeting Name | Cadence Type | Audience / Participants | Frequency | Owner | Purpose / Objective | Key Output / Artifact | Duration | Status | Last Held On | Next Scheduled Date | Notes

## Resource Management Plan
Zapcom ID | Resource Name | Role | Workstream / Function | Allocation % | Start Date | End Date | Status | Criticality | Primary Manager / Lead | Backup / Secondary Owner | Notes | Allocation Status
| Santhosh Nebalan |  | INDIA | [8 empty] | Unassigned
| Poornima Bhakthavachalam | [10 empty] | Unassigned
| Sneha Reddy | [10 empty] | Unassigned
| Sravanthi Palavalli | [10 empty] | Unassigned
| Ajay Kumar Yadalapalli | [10 empty] | Unassigned
| Malatesh Adakayavar | [10 empty] | Unassigned
| Suresh Kuruva | [10 empty] | Unassigned
| Lavanya Uppala | [10 empty] | Unassigned
ZC00340 | Atul Kalokhe | [10 empty] | Unassigned

## RACI Matrix
RACI MATRIX |  |  | Project Leader 1 | Project Leader 2 | Project Leader 3 | Project Leader 4 | Project Leader 5 | Team Member 1 | Team Member 2 | Team Member 3 | Team Member 4 | Team Member 5 | Team Member 6 | Team Member 7 | Team Member 8 | Team Member 9 | Team Member 10 | External Member 1 | External Member 2 | External Member 3 | External Member 4 | External Member 5
PRIORITY | STATUS | PROJECT DELIVERABLE | Project Leadership |  |  |  |  | Team 1 |  |  |  |  | Team 2 |  |  |  |  | Other
PHASE 1 - Initiation
Low | In Progress | Request Review by PMO
Medium | Complete | Create Project Charter
High | Needs Review | Build Deliverables
PHASE 2 - Planning and Design
PHASE 3 - Execution and Monitoring
PHASE 4 - Closing

## Resource Availability
Availability ID | Resource ID | Resource Name | Unavailability Type | Start Date | End Date | Days Impacted | Backup Assigned | Impact Level | Status | Notes
RAV-001
RAV-002
RAV-003
RAV-004
RAV-005
RAV-006
RAV-007
RAV-008
RAV-009
RAV-010

## Change Management Plan
Change ID | Date Submitted | Requester | Change Description | Reason / Driver | Impacted Area / Deliverable | Impact Summary | Priority | Owner | Status | Decision | Decision Date | Target Implementation Date | Follow-up / Notes
1 |  |  | asdf

## Project Plan
Task ID | WBS | Phase | Task Name | Task Type | Predecessor ID | Owner | Support Team / Function | Planned Start Date | Planned End Date | Duration (Days) | Actual Start Date | Actual End Date | Status | % Complete | Add to Milestone Tracker | Baseline Start Date | Baseline End Date | Variance (Days) | RAG Status | Comments / Notes | _MilestoneSeq
T-001 | 1.0 | Initiation | Project Kickoff | Milestone |  | Project Manager | PMO | 2026-04-01 | 2026-04-01 | 1 |  |  | Completed | 100% | ☑ | 2026-04-01 | 2026-04-01 | 0 | Amber | Formal kickoff with sponsor and core team | 1
T-002 | 1.1 | Planning | Requirements Finalization | Task | T-001 | Business Analyst | Business / Product | 2026-04-02 | 2026-04-08 | 7 |  |  | In Progress | 60% | ☐ | 2026-04-02 | 2026-04-08 | 0 | Green | Freeze scope and confirm requirements
T-003 | 1.2 | Planning | Solution Design Sign-off | Milestone | T-002 | Solution Architect | Engineering | 2026-04-10 | 2026-04-10 | 1 |  |  | Completed | 0% | ☑ | 2026-04-10 | 2026-04-10 | 0 | Red | Design sign-off required before build | 2
T-004 | 2.0 | Execution | Build & Configuration | Task | T-003 | Engineering Lead | Engineering | 2026-04-11 | 2026-04-24 | 14 |  |  | Not Started | 0% | ☐ | 2026-04-11 | 2026-04-24 | 0 | Green | Core build and configuration activities
T-005 | 3.0 | Deployment | Go-Live | Milestone | T-004 | Project Manager | Cross-functional | 2026-05-01 | 2026-05-01 | 1 |  |  | Not Started | 0% | ☑ | 2026-05-01 | 2026-05-01 | 0 | Green | Production deployment milestone | 3
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
Formulas:
RAG Status = IF([Task ID]="","",IF([Status]="Completed","Amber",IF(AND([Planned End Date]<>"",TODAY()>[Planned End Date]),"Red",IF(AND([Planned End Date]<>"",TODAY()+3>=[Planned End Date]),"Amber","Green"))))
RAG Status = IF([Task ID]="","",IF([Status]="Completed","Red",IF(AND([Planned End Date]<>"",TODAY()>[Planned End Date]),"Red",IF(AND([Planned End Date]<>"",TODAY()+3>=[Planned End Date]),"Amber","Green"))))

## Milestone Tracker
Milestone Ref | WBS | Phase | Milestone / Task Name | Owner | Planned Start Date | Planned End Date | Actual End Date | Status | % Complete | Baseline End Date | Variance (Days) | RAG Status | Notes | _MilestoneSeq
T-001 | 1.0 | Initiation | Project Kickoff | Project Manager | 2026-04-01 | 2026-04-01 | 0 | Completed | 100% | 2026-04-01 | 0 | Amber | Formal kickoff with sponsor and core team | 1
T-003 | 1.2 | Planning | Solution Design Sign-off | Solution Architect | 2026-04-10 | 2026-04-10 | 0 | Completed | 0% | 2026-04-10 | 0 | Red | Design sign-off required before build | 2
T-005 | 3.0 | Deployment | Go-Live | Project Manager | 2026-05-01 | 2026-05-01 | 0 | Not Started | 0% | 2026-05-01 | 0 | Green | Production deployment milestone | 3