## Portfolio V1 Metrics
Metric Name | Metric Description | Metric Formula (pseudo) | Bucket | Area / Source | User Type(s) | Refresh Cadence | Thresholds / Notes
Total Active Projects | Count of projects currently in active delivery (not Closed/On Hold). | COUNTIFS(Projects[Status], "Active") | Portfolio Health | Project Register / Cover | Leadership, PMO | Daily | Define 'Active' statuses centrally.
Projects by RAG Status (G/A/R) | Number of active projects by overall health (Green/Amber/Red). | COUNTIFS(Projects[RAG], "Green", Projects[Status], "Active") (repeat for Amber/Red) | Portfolio Health | Status / Cover | Leadership, PMO | Weekly | RAG rules should be consistent across projects.
Projects Updated This Week | Count of projects with a status update within the last 7 days. | COUNTIFS(Projects[LastUpdateDate], ">="&TODAY()-7, Projects[Status], "Active") | Governance | Status / Governance | PMO | Daily | Use business calendar if needed.
Projects Missing Weekly Update | Count of active projects where last update is older than 7 days. | COUNTIFS(Projects[LastUpdateDate], "<"&TODAY()-7, Projects[Status], "Active") | Governance | Status / Governance | PMO, Leadership | Daily | Escalate if >0 for more than 2 days.
Overdue Milestones (Total) | Total number of milestones past due and not completed across all active projects. | COUNTIFS(Milestones[DueDate], "<"&TODAY(), Milestones[Status], "<>Complete", Milestones[ProjectStatus], "Active") | Schedule & Milestones | Milestones | Leadership, PMO | Daily | Exclude 'Cancelled/Descoped' milestones.
Projects with ≥1 Overdue Milestone | Number of active projects that have at least one overdue milestone. | DISTINCTCOUNT(Milestones[ProjectID] WHERE DueDate<TODAY AND Status<>"Complete" AND ProjectStatus="Active") | Schedule & Milestones | Milestones | Leadership, PMO | Daily | Compute distinct projects in app logic (not an Excel formula).
Upcoming Milestones (Next 14 Days) | Count of milestones due within the next 14 days (not complete). | COUNTIFS(Milestones[DueDate], ">="&TODAY(), Milestones[DueDate], "<="&TODAY()+14, Milestones[Status], "<>Complete") | Schedule & Milestones | Milestones | Leadership, PMO | Daily | Use 7/14/30-day toggles.
Open Critical Risks | Count of open risks rated Critical/High across active projects. | COUNTIFS(RAID[Type],"Risk", RAID[Severity],"High", RAID[Status],"Open", RAID[ProjectStatus],"Active") | RAID / Escalation | RAID | Leadership, PMO | Daily | Define severity scale (High/Med/Low).
Open Critical Issues | Count of open issues rated Critical/High across active projects. | COUNTIFS(RAID[Type],"Issue", RAID[Severity],"High", RAID[Status],"Open", RAID[ProjectStatus],"Active") | RAID / Escalation | RAID | Leadership, PMO | Daily | Highlight items older than X days.
Open Escalations | Count of items flagged as escalated (and not closed) across portfolio. | COUNTIFS(RAID[Escalated],"Yes", RAID[Status],"Open", RAID[ProjectStatus],"Active") | RAID / Escalation | RAID / Actions | Leadership, PMO | Daily | Escalation criteria should be documented.
Governance Compliance % | Percent of required governance events completed on time (e.g., weekly status, steering). | CompletedOnTime / PlannedInPeriod | Governance | Governance & Cadences | PMO, Leadership | Weekly | Target ≥90% (example).
Planned vs Actual Progress (Portfolio Variance) | Gap between planned completion % and actual completion % across active projects. | AVG(Projects[Actual%]) - AVG(Projects[Planned%]) | Schedule & Milestones | Project Plan / Status | Leadership, PMO | Weekly | Negative variance indicates behind schedule.

## Portfolio Secondary
Metric Name | Metric Description | Metric Formula (pseudo) | Bucket | Area / Source | User Type(s) | Refresh Cadence | Thresholds / Notes
Milestone Slippage Trend (30/60/90 days) | Trend of average milestone slip days over time across portfolio. | AVG(Milestones[ActualDate]-Milestones[BaselineDate]) by month | Schedule & Milestones | Milestones | PMO, Leadership | Weekly | Requires baseline date capture.
Risk Aging (Median Days Open) | Median number of days open for risks across portfolio. | MEDIAN(TODAY()-RAID[CreatedDate]) where Type=Risk and Status=Open | RAID / Escalation | RAID | PMO | Weekly | Flag risks open >30 days.
Issue Aging (Median Days Open) | Median number of days open for issues across portfolio. | MEDIAN(TODAY()-RAID[CreatedDate]) where Type=Issue and Status=Open | RAID / Escalation | RAID | PMO | Weekly | Flag issues open >14 days (example).
Action Closure Rate | Percentage of action items closed within SLA (e.g., 7 days). | ClosedWithinSLA / TotalClosedInPeriod | Governance | Actions / Governance | PMO | Weekly | Requires action created & closed dates.
Decision Cycle Time (Avg Days) | Average days from decision logged to decision closed. | AVG(Decisions[ClosedDate]-Decisions[CreatedDate]) | Governance | Decisions / Governance | Leadership, PMO | Monthly | Helps identify governance bottlenecks.
Resource Utilization (Portfolio) | Average utilization across resources (planned or actual). | SUM(Effort[Hours]) / SUM(Effort[CapacityHours]) | Resource / Effort | Effort Tracking | PMO, Delivery Leadership | Weekly | Needs agreed capacity model.
Overallocated Resources (#) | Count of people over capacity in the period. | COUNTIFS(Resources[Utilization%], ">"&1.0) | Resource / Effort | Effort Tracking / Resource Plan | PMO, Delivery Leadership | Weekly | Over 100% planned capacity.
Change Requests (Count) | Number of change requests submitted/approved in the period. | COUNTIFS(Changes[CreatedDate],">="&Start, Changes[CreatedDate],"<="&End) | Portfolio Health | Change Control | Leadership, PMO | Monthly | Optional if change log exists.
Budget Variance (Portfolio) | Aggregate budget variance across projects (if financials tracked). | SUM(Projects[ActualCost]) - SUM(Projects[Budget]) | Portfolio Health | Financials | Leadership, PMO | Monthly | Only if budget/cost fields are maintained.
Forecast Accuracy (Schedule) | How accurate project completion forecasts are (planned vs actual). | AVG(ABS(Projects[ForecastEnd]-Projects[ActualEnd])) in days | Schedule & Milestones | Project Plan / Milestones | PMO | Monthly | Requires forecast and actual end dates.

## Project V1 Metrics
Metric Name | Metric Description | Metric Formula (pseudo) | Bucket | Area / Source | User Type(s) | Refresh Cadence | Thresholds / Notes
Project RAG Status | Overall project health (Green/Amber/Red) based on agreed rules. | Derived from rules (schedule variance, RAID severity, governance misses) | Portfolio Health | Status / Cover | PM, Delivery Lead, Leadership | Weekly | Make rules explicit to avoid subjective RAG.
Project % Complete (Tasks) | Percent of tasks completed out of total tasks in plan. | COUNTIFS(Tasks[Status],"Complete") / COUNTA(Tasks[TaskID]) | Schedule & Milestones | Project Plan | PM, Delivery Lead | Daily | Exclude cancelled tasks.
Planned vs Actual Progress Variance | Difference between planned completion % and actual completion % for the project. | Project[Actual%] - Project[Planned%] | Schedule & Milestones | Project Plan / Status | PM, PMO | Weekly | Negative = behind plan.
Milestone Completion % | Completed milestones / total milestones for the project. | COUNTIFS(Milestones[Status],"Complete") / COUNTA(Milestones[MilestoneID]) | Schedule & Milestones | Milestones | PM, Delivery Lead, Leadership | Weekly | Exclude cancelled milestones.
Upcoming Milestones (Next 14 Days) | Milestones due in the next 14 days (not complete). | COUNTIFS(Milestones[DueDate],">="&TODAY(), Milestones[DueDate],"<="&TODAY()+14, Milestones[Status],"<>Complete") | Schedule & Milestones | Milestones | PM, Delivery Lead | Daily | Use 7/14/30-day toggles.
Overdue Milestones | Milestones past due date and not complete for the project. | COUNTIFS(Milestones[DueDate],"<"&TODAY(), Milestones[Status],"<>Complete") | Schedule & Milestones | Milestones | PM, Delivery Lead, PMO | Daily | Escalate if any critical milestone is overdue.
Overdue Tasks | Tasks past end date and not complete. | COUNTIFS(Tasks[EndDate],"<"&TODAY(), Tasks[Status],"<>Complete") | Schedule & Milestones | Project Plan | PM, Delivery Lead | Daily | Consider excluding 'Not Started' vs 'In Progress' separately.
Open Risks (High Severity) | Count of open high severity risks for the project. | COUNTIFS(RAID[Type],"Risk", RAID[Severity],"High", RAID[Status],"Open") | RAID / Escalation | RAID | PM, PMO, Leadership | Daily | Show top 5 risks by severity/impact.
Open Issues (High Severity) | Count of open high severity issues for the project. | COUNTIFS(RAID[Type],"Issue", RAID[Severity],"High", RAID[Status],"Open") | RAID / Escalation | RAID | PM, PMO, Leadership | Daily | Show oldest issues first.
Aged RAID Items (>30 days) | Count of RAID items open for more than 30 days. | COUNTIFS(RAID[Status],"Open", RAID[CreatedDate],"<"&TODAY()-30) | RAID / Escalation | RAID | PM, PMO | Weekly | 30 days configurable.
Governance Compliance (Project) | Percent of planned governance events completed on time for this project. | CompletedOnTime / PlannedInPeriod | Governance | Governance & Cadences | PM, PMO | Weekly | Target ≥90% (example).
Last Status Update Age (Days) | Days since last status update was posted. | TODAY() - Project[LastUpdateDate] | Governance | Status / Governance | PM, PMO | Daily | If >7 days, flag.

## Project Secondary
Metric Name | Metric Description | Metric Formula (pseudo) | Bucket | Area / Source | User Type(s) | Refresh Cadence | Thresholds / Notes
Milestone Slippage (Avg Days) | Average milestone slip days for completed milestones (Actual vs Baseline). | AVG(Milestones[ActualDate]-Milestones[BaselineDate]) where Status=Complete | Schedule & Milestones | Milestones | PM, PMO | Weekly | Requires baseline date capture.
Schedule Variance (Days) | Variance between forecast end date and baseline end date for the project. | Project[ForecastEnd] - Project[BaselineEnd] (in days) | Schedule & Milestones | Project Plan | PM, Leadership, PMO | Weekly | Positive = later than baseline.
Risk Exposure Score | Weighted risk score using probability x impact (sum across open risks). | SUM(Risks[Probability]*Risks[Impact]) where Status=Open | RAID / Escalation | RAID (Risk) | PM, PMO | Weekly | Standardize scales (1-5).
Risk Burn-down Trend | Change in number of open risks over time (trend line). | COUNT(OpenRisks) by week | RAID / Escalation | RAID (Risk) | PM, PMO | Weekly | Useful once logging discipline is consistent.
Action Closure SLA % (Project) | Percent of actions closed within SLA (e.g., 7 days). | ClosedWithinSLA / TotalClosedInPeriod | Governance | Actions / Governance | PM, PMO | Weekly | Requires action created & closed dates.
Dependency Aging (Median Days) | Median days open for dependencies. | MEDIAN(TODAY()-Dependencies[CreatedDate]) where Status=Open | RAID / Escalation | RAID (Dependency) | PM, Delivery Lead | Weekly | Flag dependencies >14 days (example).
Effort Variance % | Planned hours vs actual hours variance (if time/effort tracked). | (SUM(ActualHours)-SUM(PlannedHours)) / SUM(PlannedHours) | Resource / Effort | Effort Tracking | PM, Delivery Lead, PMO | Weekly | Only if effort data is maintained.
Workload Burn-down | Remaining work vs time (planned vs actual burn-down). | RemainingHours by week | Resource / Effort | Effort Tracking / Project Plan | PM, Delivery Lead | Weekly | Needs remaining estimates.
Change Requests (Project) | Count of scope change requests and their status (submitted/approved). | COUNTIFS(Changes[ProjectID],this, Changes[Status],"Submitted") (repeat by status) | Portfolio Health | Change Control | PM, Leadership, PMO | Monthly | Optional if change log exists.
Budget Variance (Project) | Actual cost vs budget for the project (if tracked). | Project[ActualCost] - Project[Budget] | Portfolio Health | Financials | Leadership, PMO, PM | Monthly | Only if budget/cost fields exist.

## Dashboard Layout
Dashboard Level | Section | Metric Name | Bucket | Phase | Primary User Type(s) | Visualization | Drill-down / Target View
Portfolio | Top Row (Exec KPIs) | Total Active Projects | Portfolio Health | V1 | Leadership, PMO | KPI Tile | Portfolio Projects List
Portfolio | Top Row (Exec KPIs) | Projects by RAG Status (G/A/R) | Portfolio Health | V1 | Leadership, PMO | Stacked Bar | Portfolio Projects List (filtered)
Portfolio | Top Row (Exec KPIs) | Open Escalations | RAID / Escalation | V1 | Leadership, PMO | KPI Tile | Escalations List
Portfolio | Top Row (Exec KPIs) | Governance Compliance % | Governance | V1 | Leadership, PMO | Gauge | Governance Compliance Details
Portfolio | Delivery Health | Overdue Milestones (Total) | Schedule & Milestones | V1 | Leadership, PMO | KPI Tile | Milestones (overdue)
Portfolio | Delivery Health | Upcoming Milestones (Next 14 Days) | Schedule & Milestones | V1 | Leadership, PMO | KPI Tile | Milestones (upcoming)
Portfolio | Delivery Health | Planned vs Actual Progress (Portfolio Variance) | Schedule & Milestones | V1 | Leadership, PMO | Line/Bar | Progress Variance by Project
Portfolio | Risk & Governance | Open Critical Risks | RAID / Escalation | V1 | Leadership, PMO | KPI Tile | Risks (critical)
Portfolio | Risk & Governance | Open Critical Issues | RAID / Escalation | V1 | Leadership, PMO | KPI Tile | Issues (critical)
Portfolio | Risk & Governance | Projects Missing Weekly Update | Governance | V1 | PMO, Leadership | KPI Tile | Projects (missing updates)
Portfolio | Trends (Secondary) | Milestone Slippage Trend (30/60/90 days) | Schedule & Milestones | Secondary | PMO, Leadership | Line Chart | Milestone Slippage Details
Portfolio | Trends (Secondary) | Risk Aging (Median Days Open) | RAID / Escalation | Secondary | PMO | Line/Box | Risk Aging Details
Portfolio | Resources (Secondary) | Resource Utilization (Portfolio) | Resource / Effort | Secondary | PMO, Delivery Leadership | Bar/Heatmap | Resource Utilization View
Project | Top Row (Project KPIs) | Project RAG Status | Portfolio Health | V1 | PM, Delivery Lead | KPI Tile | Project Summary
Project | Top Row (Project KPIs) | Project % Complete (Tasks) | Schedule & Milestones | V1 | PM, Delivery Lead | Progress Bar | Task Plan
Project | Top Row (Project KPIs) | Milestone Completion % | Schedule & Milestones | V1 | PM, Delivery Lead | Progress Bar | Milestones
Project | Delivery Health | Planned vs Actual Progress Variance | Schedule & Milestones | V1 | PM, PMO | Line/Delta | Plan vs Actual View
Project | Delivery Health | Upcoming Milestones (Next 14 Days) | Schedule & Milestones | V1 | PM, Delivery Lead | List | Milestones (upcoming)
Project | Delivery Health | Overdue Milestones | Schedule & Milestones | V1 | PM, PMO | KPI Tile | Milestones (overdue)
Project | Delivery Health | Overdue Tasks | Schedule & Milestones | V1 | PM, Delivery Lead | KPI Tile | Task Plan (overdue)
Project | Risk & Actions | Open Risks (High Severity) | RAID / Escalation | V1 | PM, PMO | Table | Risk Register
Project | Risk & Actions | Open Issues (High Severity) | RAID / Escalation | V1 | PM, PMO | Table | Issue Log
Project | Risk & Actions | Aged RAID Items (>30 days) | RAID / Escalation | V1 | PM, PMO | KPI Tile | RAID Aging List
Project | Governance | Governance Compliance (Project) | Governance | V1 | PM, PMO | Gauge | Cadence Tracker
Project | Governance | Last Status Update Age (Days) | Governance | V1 | PM, PMO | KPI Tile | Status History
Project | Trends (Secondary) | Risk Burn-down Trend | RAID / Escalation | Secondary | PM, PMO | Line Chart | Risk Trend View
Project | Resources (Secondary) | Effort Variance % | Resource / Effort | Secondary | PM, Delivery Lead | Bar/Delta | Effort Tracking
Project | Schedule (Secondary) | Schedule Variance (Days) | Schedule & Milestones | Secondary | PM, Leadership, PMO | Delta | Schedule Baseline View